## Wood Buffalo Environmental Serv
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Health | Comments
Project Initiation and Discovery
Kick Off Call | 0.25d | 2022-01-31 | 2022-01-31 |  | Jasmine Singh-Ledoux | 100% | Complete | Green
Establish Access Needed | 2d | 2022-01-31 | 2022-02-01 |  | Chris Tornabene |  | Complete | Green
Discovery Incremental | 1d | 2022-02-01 | 2022-02-01 |  | Chris Tornabene |  | Complete | Green | • Short audit to discovery any environmental changes o Includes on-prem to AWS networking discovery
Buid
Architectural Design Approval | 1d | 2022-02-02 | 2022-02-02 |  |  |  | Complete
Fortinet appliance order | 6d | 2022-02-08 | 2022-02-15 |  |  |  | Complete | Green | pending appliance setup
Network testing (Test VM) | 1d | 2022-02-16 | 2022-02-16 |  | heather Hitchler |  | Complete | Green | EC2
Establish secondary VPN tunnel to AWS if necessary | 9d | 2022-02-14 | 2022-02-24 |  | Anand Dandupati |  | In Progress | Red | Secondary Tunnel is not working - On Prem Limitation - Need VGP configured on their FortiGate (Or SD-WAN Configured) SD-WAN SO IN PROGRESS : Scope will be added
Build out Active Directory extension into AWS | 3d | 2022-03-01 | 2022-03-03 |  | Anand Dandupati |  | Complete | Green
Test migrations | 6d | 2022-03-04 | 2022-03-11 | 10 | Anand Dandupati |  | In Progress |  | 1 test vm on prem - already ready - Chris to share details
Configure SSO | 3d | 2022-03-14 | 2022-03-16 | 11 | Anand Dandupati |  | In Progress |  | User list provided and is in our Teams (16 users) Pre Req's: Need additional creds of Azure AD + Jacob needs to confirm Azure AD set up
Migrations
DNS Migration to Route 53 | 1d | 2022-03-17 | 2022-03-17 | 12 | Anand Dandupati |  | Not Started |  | done with Jacob/ cutover date to choose / after hours - Host file in Teams - Discussion with Jacob Needed
VM migrations | 16d | 2022-03-18 | 2022-04-08 |  | Anand Dandupati |  | Not Started |  | List in Teams
VMs will be removed and added to AD throughout process | 1d | 2022-03-18 | 2022-03-18 | 14 | Anand Dandupati |  | Not Started
Low-impact migrations | 5d | 2022-03-21 | 2022-03-25 | 16 | Anand Dandupati |  | Not Started |  | Chris has the list of Ranked VMs/ RIsk to Flag - timeline might extend
High-impact VM migrations | 5d | 2022-03-28 | 2022-04-01 | 17 | Anand Dandupati |  | Not Started |  | risk: timeline might extent
Cleanup | 3d | 2022-04-04 | 2022-04-06 | 18 | Anand Dandupati |  | Not Started
Configure Backup within AWS for the migrated EC2's | 1d | 2022-04-07 | 2022-04-07 | 19 | Anand Dandupati |  | Not Started
Close
Knowledge transfer and documentation | 1d | 2022-04-07 | 2022-04-07 | 19 | Heather |  | Not Started |  | Include managed services team (Chris A. Jay) (handoff call) Heather Lucid Chart Documentation - AWS Resource Diagram Zone File from Route 53/ book time to go over
Project closeout | 1d | 2022-04-08 | 2022-04-08 | 22 | Jasmine Singh-Ledoux |  | Not Started